## ClickUp Import
List (Sprint) | Task ID | Task Name | Description | Priority | Status | Tags | Duration | Dependencies
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.1 | Install & configure Claude Agent SDK | Install @anthropic-ai/claude-agent-sdk (TypeScript). Set up environment variables, API keys, SDK initialization. | High | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.2 | Create /api/journey/chat route | Implement streamText() with Opus 4.6, adaptive thinking, and toUIMessageStreamResponse(). | High | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.3 | Define Lead Agent system prompt | AI-GOS personality, strategic depth, conversation guidelines. Cache with cache_control: ephemeral. | High | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.4 | Implement tool framework | Define tool schemas with inputSchema + strict: true. Wire tool execution loop. | High | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.5 | Build SSE streaming pipeline | Map Agent SDK stream events to frontend useChat transport. Handle thinking_delta, text_delta, tool_use events. | Normal | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.6 | Create /journey page shell | Centered chat layout (~720px max-width). Basic message rendering with useChat hook. | Normal | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.7 | Implement prompt caching | System prompt + tool definitions cached on turn 1. Measure cache hit rates. | Normal | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.8 | Build cost tracking hooks | PostToolUse hook logs token usage per request. Dashboard-ready metrics. | Low | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.9 | Set up session management | Store session_id in Supabase on init. Basic resume capability. | Normal | To Do | Sprint 1 | 4-5 days | None
Sprint 1: Foundation: Agent SDK + Lead Agent | T1.10 | E2E smoke test | User sends message → Opus responds with streaming → tool call works → response completes. | High | To Do | Sprint 1 | 4-5 days | None
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.1 | Design askUser tool schema | Define the askUser tool with question, options (2-4), multi-select flag. inputSchema + strict: true. | High | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.2 | Build askUser frontend renderer | Render askUser tool calls as styled cards with tappable option chips. 'Other' option for free text. Wire response back as tool result. | High | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.3 | Design 8-question onboarding flow | Map 9 form steps to 7-9 smart questions. Define context-aware suggestion logic for each question. | High | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.4 | Implement context-aware suggestions | Each question's options are informed by prior answers. E.g., after 'SaaS' → budget options tailored to SaaS benchmarks. | High | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.5 | Build progress indicator | Thin progress bar showing onboarding phase + question count (e.g., 'Question 3 of 8'). | Normal | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.6 | Handle edge cases | Vague 'Other' answers get follow-up. Incomplete data triggers clarification. Skip warnings about impact on quality. | Normal | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.7 | Onboarding completion detection | Lead Agent determines when enough info is gathered. Transitions to 'Generating your blueprint...' phase. | Normal | To Do | Sprint 2 | 3-4 days | S1
Sprint 2: Conversational Onboarding (askUser Pattern) | T2.8 | Regression test: 3 company profiles | Run full onboarding with 3 different company types. Verify all required data is captured via askUser flow. | High | To Do | Sprint 2 | 3-4 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.1 | Build industry-researcher sub-agent | Sonar Pro model. WebSearch + WebFetch tools. Returns IndustrySchema with market size, trends, dynamics, regulatory, citations. | High | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.2 | Build competitor-researcher sub-agent | Sonar Pro + Sonnet 4.6. Discovers competitors, profiles each with positioning, pricing, strengths, weaknesses. | High | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.3 | Build ICP-analyst sub-agent | Sonnet 4.6 (high effort). Takes onboarding data + industry research. Returns ICP schema with segments, psychographics, pain/desire matrix. | High | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.4 | Build offer-analyst sub-agent | Sonnet 4.6 (high effort). 6-dimension scoring, red flags, go/no-go. Validates against ICP and competitor data. | Normal | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.5 | Build MCP servers (Firecrawl, SpyFu, AdLibrary, PageSpeed) | 4 MCP tool servers with HTTP transport. Each with 2-3 tools. Wire into Agent SDK initialization. | High | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.6 | Implement parallel sub-agent dispatch | Lead Agent calls 2-3 research tools in one response. SDK executes in parallel. | Normal | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.7 | Build structured output validation | Every sub-agent output validated against Zod schema. Retry on failure with error context. | Normal | To Do | Sprint 3 | 4-5 days | S1
Sprint 3: Research Sub-Agents + MCP Servers | T3.8 | Tool verification: 100% PASS | Every MCP tool makes a real API call and returns valid data. All sub-agents produce schema-valid output. | High | To Do | Sprint 3 | 4-5 days | S1
Sprint 4: Section Generation + Inline Cards | T4.1 | Build section card component | Header with title + status badge + section icon. Streaming markdown content. Expand/collapse. | High | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.2 | Implement section color coding + action row | Color-coded cards (blue/green/purple/orange/fuchsia). Approve/Edit/Question/Regenerate buttons. | Normal | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.3 | Implement section streaming | Content streams token-by-token into card as sub-agent generates it. Real-time rendering. | High | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.4 | Build validation loop | After card renders, Lead Agent waits for user action. Approve → next. Edit → modify + re-render. Question → answer. | High | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.5 | Implement cross-section context | Each validated section added to Lead Agent context with cache_control. Later sections see earlier validated output. | Normal | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.6 | Build section progress tracker | Progress bar: 'Phase 2: Competitor Intelligence • 3/10 sections.' | Low | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 4: Section Generation + Inline Cards | T4.7 | Regression test: 5 core sections E2E | Generate Industry, ICP, Competitors, Offer, Cross-Analysis with full validation loop. | High | To Do | Sprint 4 | 4-5 days | S2 + S3
Sprint 5: Media Plan + Unified Journey | T5.1 | Extend Lead Agent for media plan phase | Transition language, new tool introductions, budget-aware reasoning. | High | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.2 | Build 5 media plan section sub-agents | Platform Strategy, Targeting Matrix, KPI Framework, Campaign Structure, Budget Allocation. | High | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.3 | Implement deterministic budget calculator | Mathematical model (not AI) based on CAC targets, platform CPMs, validated ICP data. | Normal | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.4 | Build performance projection model | Uses validated data (ICP size, competitor spend, keyword CPCs) for realistic KPI projections. | Normal | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.5 | Wire media plan into inline card system | Same approve/edit/question flow as research sections. | Normal | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.6 | Cross-analysis synthesis (Opus max effort) | Opus 4.6 synthesizes all 10 sections into coherent cross-referenced analysis. | High | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.7 | Journey completion flow | Final summary, key recommendations, next steps. Journey-complete SSE event. | Normal | To Do | Sprint 5 | 3-4 days | S4
Sprint 5: Media Plan + Unified Journey | T5.8 | Regression test: full 10-section journey | Onboarding → research → media plan → cross-analysis end-to-end. | High | To Do | Sprint 5 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.1 | Implement Supabase journey store | Save validated sections + conversation state after each approval. Schema: journeys, journey_sections, journey_messages. | High | To Do | Sprint 6 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.2 | Build resume flow | Load session from Supabase → restore Agent SDK session → resume from last validated section. | High | To Do | Sprint 6 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.3 | Implement auto-save + journey list page | PreCompact hook archives transcript. Journey list shows status, completion %, last activity. | Normal | To Do | Sprint 6 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.4 | Build DOCX + PDF export | Generate professional Word doc from validated sections. PDF via LibreOffice headless. | Normal | To Do | Sprint 6 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.5 | Build sharing capability | Generate shareable link for read-only journey view. Client sees the full blueprint. | Low | To Do | Sprint 6 | 3-4 days | S4
Sprint 6: Persistence, Resume, Export | T6.6 | Regression test: resume + export | Start → complete 3 sections → close browser → resume → complete remaining → export. | High | To Do | Sprint 6 | 3-4 days | S4
Sprint 7: Polish, Testing, Launch | T7.1 | Client testing: 5 real profiles | Run 5 real client profiles through full journey. Document quality, timing, cost. | High | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.2 | Streaming + parallelism optimization | Reduce time-to-first-token. Maximize parallel sub-agent execution. | Normal | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.3 | Error handling + graceful degradation | Enrichment API failures don't block journey. Lead Agent adapts messaging. | High | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.4 | Cost optimization | Review actual token usage per journey. Tune effort levels. Enable Batch API where applicable. | Normal | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.5 | Build monitoring dashboard | Per-journey: cost, time, section count, validation rate, error rate. | Low | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.6 | Production deployment | Vercel Pro with 300s timeout. Environment variables. Edge config for long-running routes. | High | To Do | Sprint 7 | 3-4 days | S5 + S6
Sprint 7: Polish, Testing, Launch | T7.7 | Final E2E: 3 journeys on production | Cold start to export on production. All pass. Cost within budget. | High | To Do | Sprint 7 | 3-4 days | S5 + S6

## Sprint Overview
Sprint | Name | Duration | Week | Tasks | Dependencies | Priority | Status
S1 | Foundation: Agent SDK + Lead Agent | 4-5 days | Week 1 | 10 | None | Urgent | To Do
S2 | Conversational Onboarding (askUser Pattern) | 3-4 days | Week 1-2 | 8 | S1 | High | To Do
S3 | Research Sub-Agents + MCP Servers | 4-5 days | Week 2 | 8 | S1 | High | To Do
S4 | Section Generation + Inline Cards | 4-5 days | Week 2-3 | 7 | S2 + S3 | High | To Do
S5 | Media Plan + Unified Journey | 3-4 days | Week 3 | 8 | S4 | Normal | To Do
S6 | Persistence, Resume, Export | 3-4 days | Week 4 | 6 | S4 | Normal | To Do
S7 | Polish, Testing, Launch | 3-4 days | Week 5 | 7 | S5 + S6 | Normal | To Do

## Setup Guide
HOW TO IMPORT INTO CLICKUP
Step 1: Create a Space | Create a new Space called 'AI-GOS v2' in your ClickUp workspace
Step 2: Create a Folder | Inside the Space, create a Folder called 'Development Sprints'
Step 3: Create 7 Lists | Create one List per sprint inside the Folder:
• Sprint 1: Foundation: Agent SDK + Lead Agent
• Sprint 2: Conversational Onboarding (askUser Pattern)
• Sprint 3: Research Sub-Agents + MCP Servers
• Sprint 4: Section Generation + Inline Cards
• Sprint 5: Media Plan + Unified Journey
• Sprint 6: Persistence, Resume, Export
• Sprint 7: Polish, Testing, Launch
Step 4: Import Tasks | In each List, click '...' → Import → CSV/Excel
Filter the 'ClickUp Import' sheet by Sprint column, copy those rows
Map columns: Task Name → Name, Description → Description, Priority → Priority
Step 5: Add Dependencies | After import, add task dependencies based on the Dependencies column
ALTERNATIVE: Quick Manual Setup
1. Go to clickup.com → Create Space 'AI-GOS v2'
2. Add Folder 'Development Sprints'
3. For each sprint, create a List and add tasks from the 'ClickUp Import' sheet
4. Use the Task ID (T1.1, T2.3, etc.) in task titles for easy reference
5. Set priorities and dependencies as listed