AI-GOS v2.0

PROJECT ROADMAP

Development Sprints + M2C1 Methodology

Powered by Claude Code + Anthropic Agent SDK

SaaSLaunch  •  February 2026

# 1. How We Build: M2C1 + Claude Code

AI-GOS v2 is built using the M2C1 meta-orchestration framework running inside Claude Code. M2C1 turns a brain dump (our PRD) into fully built, tested software by coordinating multiple AI sub-agents through 12 planning phases, then autonomous execution. Claude Code is the runtime — it writes, tests, and deploys the code. Together, they give us 5-10x development speed because the AI handles boilerplate, research, testing, and iteration while we focus on strategic decisions.

## 1.1 What M2C1 Does For Us

M2C1 is a skill installed in Claude Code (~/.claude/skills/m2c1/). When we start a session and describe AI-GOS v2, it automatically kicks off a structured workflow:

| Phase | Name | What Happens |
| --- | --- | --- |
| 0-1 | Setup + PRD | Creates orchestration folder. Converts our existing PRD into M2C1 format. |
| 2 | First Research Wave | Parallel sub-agents research: Anthropic Agent SDK patterns, Vercel AI SDK v6, MCP server setup, Perplexity integration, Supabase schemas. |
| 3 | Discovery Questions | M2C1 generates decision-forcing questions. We answer them. These become DISCOVERY.md — the top authority document that overrides everything. |
| 4 | Second Research Wave | Implementation-focused research filtered by our discovery answers. Exact API shapes, config snippets, dependency versions. |
| 5-6 | Tool Setup + Verify | Configures MCP servers, API keys, CLIs. Verifies each tool works with real calls. 100% PASS required. |
| 7 | Skill Creation | Creates project-level skills documenting every tool, domain pattern, and testing strategy for sub-agents. |
| 8 | Context Compact | Saves all state to files. Allows fresh context window for execution. |
| 9-10 | Plan + Shard Tasks | Creates PHASES.md master plan. Expands every task into self-contained execution prompts. Each task file has everything a sub-agent needs. |
| 11-12 | Review + Execute | Cross-phase coherence check. Generates START.md. Autonomous execution begins: orchestrator spawns sub-agents per task, verifies, runs regression tests. |

Why This Matters With M2C1 + Claude Code, each sprint below isn’t “1 developer for 1 week.” It’s “Claude Code autonomously executing 15-30 self-contained tasks with regression testing.” What would take a human team 2 weeks takes 2-3 days. We focus on reviewing outputs and making strategic decisions, not writing boilerplate.

## 1.2 Our Development Cycle

For each sprint, the cycle is:

- Feed sprint scope into M2C1 as a focused brain dump

- M2C1 runs Phases 0-8 (research, discovery, tool setup, skills) — ~30-60 min

- We answer discovery questions (the only manual step) — ~15 min

- M2C1 runs Phases 9-12 (plan, shard, review, execute) — autonomous

- Sub-agents write code, tests pass, regression runs — Claude Code handles it

- We review outputs, approve, merge — move to next sprint

# 2. Roadmap Overview

The build is organized into 7 sprints across 5 weeks. Sprints are parallelizable where dependencies allow. The critical path runs through Sprints 1 → 2 → 3 → 5 → 7. Sprints 4 and 6 can run in parallel with adjacent sprints.

| # | Sprint | Duration | Week | Tasks | Dependencies |
| --- | --- | --- | --- | --- | --- |
| S1 | Foundation: Agent SDK + Lead Agent | 4-5 days | Week 1 | ~20 tasks | None (start here) |
| S2 | Conversational Onboarding | 3-4 days | Week 1-2 | ~15 tasks | S1 complete |
| S3 | Research Sub-Agents + MCP Servers | 4-5 days | Week 2 | ~25 tasks | S1 complete |
| S4 | Section Generation + Inline Cards | 4-5 days | Week 2-3 | ~20 tasks | S2 + S3 complete |
| S5 | Media Plan + Unified Journey | 3-4 days | Week 3 | ~15 tasks | S4 complete |
| S6 | Persistence, Resume, Export | 3-4 days | Week 4 | ~15 tasks | S4 complete |
| S7 | Polish, Testing, Launch | 3-4 days | Week 5 | ~15 tasks | S5 + S6 complete |

Timeline With Claude Code + M2C1 at full speed: 5 weeks total. ~125 self-contained tasks. Each task is a focused, testable unit that a Claude Code sub-agent can execute autonomously. We approve and merge, not write.

SPRINT 1 • 4-5 days • Week 1 Foundation: Agent SDK + Lead Agent Critical path — everything depends on this

This sprint establishes the core infrastructure. We set up the Claude Agent SDK, build the Lead Agent route, wire adaptive thinking, and get a basic streaming chat working end-to-end. Nothing else can start until this is solid.

### Tasks

- T1.1: Install and configure @anthropic-ai/claude-agent-sdk (TypeScript). Set up environment variables, API keys, and SDK initialization.

- T1.2: Create /api/journey/chat route. Implement streamText() with Opus 4.6, adaptive thinking, and toUIMessageStreamResponse().

- T1.3: Define Lead Agent system prompt. AI-GOS personality, strategic depth, conversation guidelines. Cache with cache_control: ephemeral.

- T1.4: Implement basic tool framework. Define tool schemas with inputSchema + strict: true. Wire tool execution loop.

- T1.5: Build SSE streaming pipeline. Map Agent SDK stream events to frontend useChat transport. Handle thinking_delta, text_delta, tool_use events.

- T1.6: Create /journey page shell. Centered chat layout (~720px max-width). Basic message rendering with useChat hook.

- T1.7: Implement prompt caching layer. System prompt + tool definitions cached on turn 1. Measure cache hit rates.

- T1.8: Build cost tracking hooks. PostToolUse hook logs token usage per request. Dashboard-ready metrics.

- T1.9: Set up session management. Store session_id in Supabase on init. Basic resume capability.

- T1.10: End-to-end smoke test. User sends message → Opus responds with streaming → tool call works → response completes.

### Acceptance Criteria

- Lead Agent responds conversationally with streaming text

- Adaptive thinking activates on complex questions (visible in logs)

- At least one tool call executes and returns results

- Prompt caching shows cache_read_input_tokens > 0 on turn 2+

- Session ID persisted to Supabase

SPRINT 2 • 3-4 days • Week 1-2 Conversational Onboarding Replaces the 9-step form wizard with a natural conversation

The 9-step form wizard dies here. The Lead Agent now gathers all onboarding information through natural conversation — asking the right questions, pushing back on vague answers, and researching in the background.

### Tasks

- T2.1: Design conversation flow. Map the 9 form steps to 7-9 natural questions. Define question sequencing logic in Lead Agent prompt.

- T2.2: Implement question-asking tool. Lead Agent tracks which questions are answered, which are pending, what data is sufficient.

- T2.3: Build background research trigger. After Q1 (company/URL), Lead Agent kicks off Perplexity research silently while continuing the conversation.

- T2.4: Implement voice input integration. Wire existing Groq Whisper transcription into the chat input. Voice-first, text-secondary.

- T2.5: Build progress indicator component. Thin progress bar showing onboarding phase + question count.

- T2.6: Implement research activity ticker. Subtle animated text showing background research status during onboarding.

- T2.7: Build smart suggestions. Lead Agent pre-fills known data from URL research and asks user to confirm/correct.

- T2.8: Handle edge cases: vague answers (push back), incomplete data (ask follow-up), user skipping questions (warn about impact).

- T2.9: Onboarding completion detection. Lead Agent determines when enough information is gathered and transitions to section generation.

- T2.10: Regression test: full onboarding flow end-to-end with 3 different company profiles.

### Acceptance Criteria

- User completes onboarding in < 5 minutes via conversation (no forms)

- Lead Agent asks follow-ups for vague answers

- Background research runs while user chats (visible in activity ticker)

- Voice input works as primary entry method

SPRINT 3 • 4-5 days • Week 2 Research Sub-Agents + MCP Servers The intelligence layer — 7 specialist sub-agents + 4 MCP tool servers

This is the heavy infrastructure sprint. We build every research sub-agent and every MCP server that the Lead Agent dispatches work to. Each sub-agent is a specialist with its own model, tools, and output schema.

### Tasks — Sub-Agents

- T3.1: Build industry-researcher sub-agent. Sonar Pro model. WebSearch + WebFetch tools. Returns IndustrySchema with market size, trends, dynamics, regulatory, citations.

- T3.2: Build competitor-researcher sub-agent. Sonar Pro + Sonnet 4.6. Discovers competitors, profiles each with positioning, pricing, strengths, weaknesses.

- T3.3: Build icp-analyst sub-agent. Sonnet 4.6 (high effort). Takes onboarding data + industry research. Returns ICP schema with segments, psychographics, pain/desire matrix, reachability.

- T3.4: Build offer-analyst sub-agent. Sonnet 4.6 (high effort). 6-dimension scoring, red flags, go/no-go. Validates against ICP and competitor data.

- T3.5: Build messaging-strategist sub-agent. Sonnet 4.6 (high effort). Hooks, angles, proof points tied to ICP psychology and competitor gaps.

- T3.6: Build media-planner sub-agent. Sonnet 4.6 (high effort). Platform strategy, targeting, KPIs, budget allocation. Reads all prior validated sections.

- T3.7: Build seo-auditor sub-agent. Sonnet 4.6 (medium effort). Firecrawl crawl + PageSpeed API. Technical health, content gaps, keyword opportunities.

### Tasks — MCP Servers

- T3.8: Build firecrawl-mcp server. Tools: scrape_pricing_page, crawl_website, extract_structured. HTTP transport within Next.js.

- T3.9: Build spyfu-mcp server. Tools: get_keyword_data, get_competitor_keywords, get_ad_history.

- T3.10: Build adlibrary-mcp server. Tools: search_ads, get_creative_analysis, get_ad_spend_estimate.

- T3.11: Build pagespeed-mcp server. Tools: audit_url, get_core_web_vitals, get_seo_signals.

- T3.12: Wire all MCP servers into Agent SDK initialization. Tool search enabled at 10% threshold.

- T3.13: Tool verification: every MCP tool makes a real API call and returns valid data. 100% PASS required (M2C1 Phase 6 pattern).

### Tasks — Orchestration

- T3.14: Implement parallel sub-agent dispatch. Lead Agent calls 2-3 research tools in one response. SDK executes in parallel.

- T3.15: Build SubagentStart/SubagentStop hooks. Emit research-activity SSE events to frontend. Track timing.

- T3.16: Implement structured output validation. Every sub-agent output validated against Zod schema. Retry on failure.

- T3.17: Regression test: Lead Agent dispatches all 7 sub-agents with real data. All return valid schemas.

### Acceptance Criteria

- All 7 sub-agents produce schema-valid output from real inputs

- All 4 MCP servers pass real-world tool verification (100% PASS)

- Parallel dispatch executes 3+ sub-agents simultaneously

- Research activity events stream to frontend in real-time

SPRINT 4 • 4-5 days • Week 2-3 Section Generation + Inline Cards The visible output — sections render as cards in the chat flow

This sprint connects the research sub-agents to the user interface. The Lead Agent presents each section as an inline card within the chat. Users validate, request edits, or ask questions before proceeding.

### Tasks

- T4.1: Build section card component. Header with title + status badge + section icon. Streaming markdown content. Expand/collapse.

- T4.2: Implement section color coding. Blue (market), green (ICP), purple (competitors), orange (offer), fuchsia (messaging). Match existing AI-GOS visual identity.

- T4.3: Build action row. Approve (green), Request Edit (orange), Ask Question (blue), Regenerate (gray). Wire each to Lead Agent tools.

- T4.4: Implement section streaming. Content streams token-by-token into the card as the sub-agent generates it.

- T4.5: Build collapse behavior. Validated sections collapse to summary bar (title + key metric + green checkmark). Click to expand.

- T4.6: Implement synthesizeSection tool. Lead Agent calls this with all context to generate a section. Uses JSON schema output mode.

- T4.7: Implement editSection tool. Modifies specific fields within a validated section based on user feedback.

- T4.8: Build the validation loop. After section card renders, Lead Agent waits for user action. Approve → next section. Edit → modify + re-render. Question → answer then re-ask.

- T4.9: Implement cross-section context. Each validated section is added to Lead Agent context with cache_control. Later sections see earlier validated output.

- T4.10: Implement flexible schemas. Minimum counts, not exact counts. Required + optional fields. Let Opus decide depth.

- T4.11: Build section progress tracker. Progress bar updates: “Phase 2: Competitor Intelligence • 3/10 sections.”

- T4.12: Regression test: generate all 5 core research sections (Industry, ICP, Competitors, Offer, Cross-Analysis) end-to-end with validation loop.

### Acceptance Criteria

- 5 core sections generate as inline cards in the chat flow

- Section streaming shows tokens arriving in real-time

- Approve/Edit/Question flow works for each section

- Validated sections collapse and subsequent sections reference their data

- Section validation rate > 60% first-try on test data

SPRINT 5 • 3-4 days • Week 3 Media Plan + Unified Journey Extends the journey from 5 research sections to the full 10-section blueprint + media plan

The research blueprint and media plan merge into one continuous journey. After the 5 research sections are validated, the Lead Agent transitions seamlessly into media plan generation using all the validated intelligence.

### Tasks

- T5.1: Extend Lead Agent prompt for media plan phase. Transition language, new tool introductions, budget-aware reasoning.

- T5.2: Build 5 media plan section sub-agents. Platform Strategy, Targeting Matrix, KPI Framework, Campaign Structure, Budget Allocation.

- T5.3: Implement deterministic budget calculator tool. Not AI-generated — mathematical model based on CAC targets, platform CPMs, and validated ICP data.

- T5.4: Build performance projection model. Uses validated data (ICP size, competitor spend, keyword CPCs) to project realistic KPIs.

- T5.5: Wire media plan sections into the same inline card system. Same approve/edit/question flow.

- T5.6: Implement cross-analysis synthesis. Opus 4.6 with effort: “max.” Synthesizes all 10 sections into a coherent cross-referenced analysis.

- T5.7: Build journey completion flow. Final summary, key recommendations, next steps. Journey-complete SSE event.

- T5.8: Regression test: full 10-section journey end-to-end (onboarding → research → media plan → cross-analysis).

### Acceptance Criteria

- Full 10-section journey completes in < 25 minutes

- Media plan sections use validated research data (cross-references visible)

- Budget calculator produces sane numbers (CAC sanity check passes)

- Cross-analysis synthesis ties all sections together coherently

SPRINT 6 • 3-4 days • Week 4 Persistence, Resume, Export Can run in parallel with Sprint 5. Makes journeys durable and exportable.

Journeys must survive browser closures, network drops, and multi-day workflows. This sprint adds full persistence, resume capability, and professional document export.

### Tasks

- T6.1: Implement Supabase journey store. Save validated sections + conversation state after each approval. Schema: journeys, journey_sections, journey_messages.

- T6.2: Build resume flow. Load session from Supabase → restore Agent SDK session → resume conversation from last validated section.

- T6.3: Implement auto-save. PreCompact hook archives transcript to Supabase before context compaction.

- T6.4: Build journey list page. Shows all user journeys with status, completion percentage, last activity date.

- T6.5: Implement DOCX export. Generate professional Word document from all validated sections. Use existing docx-js pipeline.

- T6.6: Implement PDF export. Convert DOCX to PDF via LibreOffice headless or build direct PDF generation.

- T6.7: Build sharing capability. Generate shareable link for read-only journey view. Client can see the full blueprint.

- T6.8: Regression test: start journey → complete 3 sections → close browser → resume → complete remaining sections → export.

### Acceptance Criteria

- Journey resumes from exact last state after browser close

- DOCX and PDF exports produce professional documents

- Journey list shows all user journeys with accurate status

- Shareable link works for client viewing

SPRINT 7 • 3-4 days • Week 5 Polish, Testing, Launch Final sprint — real client testing, performance optimization, deployment

The final sprint is all about quality. We run real client data through the system, optimize performance, fix edge cases, and prepare for production deployment.

### Tasks

- T7.1: Client testing: run 5 real client profiles through the full journey. Document quality issues, timing, and cost per journey.

- T7.2: Streaming performance optimization. Reduce time-to-first-token. Optimize SSE event throughput.

- T7.3: Sub-agent parallelism optimization. Maximize parallel execution where dependencies allow. Reduce total journey time.

- T7.4: Error handling and graceful degradation. Enrichment API failures don’t block the journey. Lead Agent adapts messaging.

- T7.5: Cost optimization. Review actual token usage per journey. Tune effort levels. Enable Batch API for non-urgent sub-agents if applicable.

- T7.6: Build monitoring dashboard. Per-journey: cost, time, section count, validation rate, error rate. Uses PostToolUse hook data.

- T7.7: Implement rate limiting. Prevent API abuse. Per-user journey limits. Enrichment API rate management.

- T7.8: Production deployment. Vercel Pro with 300s timeout. Environment variables. Edge config for long-running routes.

- T7.9: Remove old v1 routes (optional — can keep behind feature flag). Clean up deprecated onboarding wizard, batch generator, static viewer.

- T7.10: Final E2E test: 3 journeys from cold start to export on production. All pass. Cost within budget.

### Acceptance Criteria

- 5 real client journeys complete successfully

- Average journey time < 20 minutes

- Average cost per journey < $4 (with caching)

- Section validation rate > 70% first-try

- Zero critical errors in production E2E test

# 3. Sprint Dependency Map

The critical path is S1 → S2+S3 (parallel) → S4 → S5+S6 (parallel) → S7. This means Sprints 2 and 3 can run simultaneously after Sprint 1, and Sprints 5 and 6 can run simultaneously after Sprint 4.

Parallel Opportunities Week 1: S1 (foundation) alone. Week 1-2: S2 (onboarding) and S3 (sub-agents) in parallel. Week 2-3: S4 (cards) after both S2+S3. Week 3-4: S5 (media plan) and S6 (persistence) in parallel. Week 5: S7 (polish) after everything.

|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 |
| --- | --- | --- | --- | --- | --- |
| Track A | S1: Foundation | S3: Sub-Agents | S4: Cards | S5: Media Plan | S7: Launch |
| Track B | S1: Foundation | S2: Onboarding |  | S6: Persistence | S7: Launch |

# 4. M2C1 Execution Protocol

For each sprint, here is the exact M2C1 execution protocol we follow:

### Phase 0-1: Setup + PRD

Feed the sprint’s scope as a brain dump. M2C1 creates the orchestration folder and converts it into a structured PRD. For Sprint 1, we feed the existing AI-GOS v2 PRD directly.

### Phase 2: First Research Wave

Sub-agents research implementation specifics: SDK patterns, API shapes, dependency versions, configuration requirements. This runs in parallel — one agent per research domain.

### Phase 3: Discovery Questions

M2C1 generates decision-forcing questions. These are the only manual intervention point. We answer, and answers become DISCOVERY.md — the top authority document. Example questions for Sprint 1: “Should the Lead Agent use streamText or generateText?” “What’s the fallback if Opus 4.6 is rate-limited?”

### Phase 5-6: Tool Setup + Verification

M2C1 configures all tools (MCP servers, API clients, test fixtures) and verifies each with real-world calls. 100% PASS required before coding starts. This catches broken APIs, wrong keys, and integration issues before they waste coding time.

### Phase 9-10: Plan + Shard

PHASES.md breaks the sprint into ordered tasks with dependencies. Phase 10 expands each task into a self-contained execution file — everything the sub-agent needs: objective, context, dependencies, implementation plan, file paths, acceptance criteria, testing protocol.

### Phase 12+: Autonomous Execution

The orchestrator reads PROGRESS.md, loads the next pending task, spawns a sub-agent with the task file, verifies completion (tests pass, acceptance criteria met), updates PROGRESS.md, and moves to the next task. Regression tests run at each phase boundary.

Key M2C1 Rule DISCOVERY.md overrides everything. If research files, skills, or CLAUDE.md contradict a discovery decision, DISCOVERY.md wins. This prevents agents from going rogue on architecture decisions we’ve already settled.

# 5. Getting Started: Sprint 1 Kickoff

Sprint 1 is the foundation. Here’s the exact M2C1 brain dump we feed to kick it off:

Sprint 1 Brain Dump for M2C1 Build the foundation for AI-GOS v2: a conversational AI journey app. Core deliverable: a working /journey page with a centered chat interface (Claude-style) powered by the Claude Agent SDK. The Lead Agent runs on Opus 4.6 with adaptive thinking. It uses streamText() + toUIMessageStreamResponse() via Vercel AI SDK. The frontend uses useChat from @ai-sdk/react. Tool definitions use inputSchema + strict: true. Prompt caching enabled on system prompt + tool definitions. Session IDs stored in Supabase. PostToolUse hooks track token usage and cost. The page should feel like talking to a senior strategist — direct, opinionated, data-first. No forms, no wizards, just conversation. Existing codebase is Next.js + Tailwind + Clerk auth + Supabase. Build within the existing project structure following conventions in CLAUDE.md.

After feeding this, M2C1 will:

- Create the orchestration folder structure in the project

- Research: Agent SDK TypeScript setup, Vercel AI SDK v6 streaming, Opus 4.6 adaptive thinking API, prompt caching mechanics

- Generate discovery questions about edge cases, error handling, model fallbacks, testing strategy

- We answer (~15 min)

- Set up tools, verify them, create project skills

- Generate PHASES.md with ~20 tasks, shard each into execution files

- Begin autonomous execution — Claude Code writes, tests, commits

End of Roadmap

AI-GOS v2.0 — Built with M2C1 + Claude Code